## page
Task Order | RO# | PO/DO # | Line Number | Status | Shipment Method | Order Fulfilment Method | Order Pickup Country | Destination Country | Recipient Name | Tracer Category | Product Category | Item SKU | Item Description | Order Entry Date | Req Delivery Date | Agreed Delivery Date | Actual Delivery Date | Estimated Delivery Date | PO Released for Fulfillment Date | Committed Goods Available Date | Actual Goods Available Date | Ordered Quantity | Unit Cost | Line Total | Shipping Charges | Shipped Quantity | Quantity To Be Filled | UOM | Pack Size | Base Unit | Base Unit Multiplier | TLP IND | Estimated Lead Time | KN Shipment Number | Entered By | Assigned Procurement Specialist | Health Element | Funding Source Detail | Status Comment | Reason Code | Reason Code Duration | Reason Code Entry Date | Reason Code Comment | Reason Code Sharepoint Link | Reason Code History
TO2 | RO10060226 |  | 1 | Sourcing Processing Tech Package |  |  |  | Mali |  | Laboratory | Laboratory Equipment | 103512XUZ01S | C-Vue Portable Liquid Chromatograph System, 1 Each | 2018-07-31 | 2018-10-31 | [6 empty] | 1 | 2950 | 2950 | 590 | 0 | 1 | UNT | 1 Each | Each | 1 | N |  |  | npapaeracleous | Natalie Papaeracleous | 313MISSION | Not Applicable | Technical Review Documents in Preparation | [5 empty] | Additional Codes
TO2 | RO10059218 |  | 1 | Pending PSM Source Processing |  |  |  | Mali | Not Applicable | Other Pharma | Malaria Pharmaceuticals | 102123AXH0DP | Amodiaquine 76.5 mg + Sulfadoxine/Pyrimethamine 250/12.5 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets | 2018-07-13 | 2019-05-15 | [6 empty] | 20000 | 13.15 | 263000 | 85100 | 0 | 20000 | PKG | 50 x 1 SP + 3 AQ Co-Blister Tablets | Treatment | 50 | N |  |  | npapaeracleous_rp |  | 313MISSION | Malaria | RO Clarified; Will be fulfilled from 2019 Stockpile order. | [5 empty] | Additional Codes
TO2 | RO10059218 |  | 2 | Pending PSM Source Processing |  |  |  | Mali | Not Applicable | Other Pharma | Malaria Pharmaceuticals | 102124AXH0DP | Amodiaquine 153 mg + Sulfadoxine/Pyrimethamine 500/25 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets | 2018-07-13 | 2019-05-15 | [6 empty] | 40000 | 14.7 | 588000 | 85100 | 0 | 40000 | PKG | 50 x 1 SP + 3 AQ Co-Blister Tablets | Treatment | 50 | N |  |  | npapaeracleous_rp |  | 313MISSION | Malaria | RO Clarified; Will be fulfilled from 2019 Stockpile order. | [5 empty] | Additional Codes
TO2 | RO10057147 | RO10057147_1 | 3 | Shipment Delivered | Air | RDC | Belgium | Mali | Not Applicable | ACTs | Malaria Pharmaceuticals | 100076AAK08W0AF | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x1 Blister Pack Tablets [Novartis] | 2018-06-06 | 2018-06-30 | 2018-08-14 | 2018-08-13 | 2018-08-05 | 2018-06-22 | 2018-06-22 | 2018-07-06 | 12067 | 10.8 | 130323.6 | 74282 | 12067 | 0 | BOX | 30 x 6x1 Blister Pack Tablets | Treatment | 30 | N | 10 | WWWE144071003808 | qferoz | Abdul Qadeer Feroz | 313MISSION | Malaria |  | AD012 | -15 | 2018-08-15 12:02 | Goods available between RDD and ADD | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_2018_Procurement/Mali-TO2-2018-ALU-RO10057147/10_Approvals?csf=1&e=DYTDpk | Additional Codes
TO2 | RO10057147 | RO10057147_1 | 4 | Shipment Delivered | Air | RDC | Belgium | Mali | Not Applicable | ACTs | Malaria Pharmaceuticals | 100076AAK08X0AF | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x2 Blister Pack Tablets [Novartis] | 2018-06-06 | 2018-06-30 | 2018-08-14 | 2018-08-13 | 2018-08-05 | 2018-06-22 | 2018-06-22 | 2018-07-06 | 6760 | 20.1 | 135876 | 74282 | 6760 | 0 | BOX | 30 x 6x2 Blister Pack Tablets | Treatment | 30 | N | 10 | WWWE144071003808 | qferoz | Abdul Qadeer Feroz | 313MISSION | Malaria |  | AD012 | -15 | 2018-08-15 12:03 | Goods available between RDD and ADD | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_2018_Procurement/Mali-TO2-2018-ALU-RO10057147/10_Approvals?csf=1&e=DYTDpk | Additional Codes
TO2 | RO10050143 | PO10008182 | 1 | Shipment Waiver Obtained | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 103199FPA05P1CT | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 30 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-10-25 |  | 2018-10-03 | 2018-06-15 | 2018-06-30 |  | 100000 | 1.7 | 170000 | 72776.5 | 100000 | 0 | UNT | 1 Set | Set | 1 | N |  | WWWE144769995135 | zkeller |  | 313MISSION | Malaria - Mission | PO-ORDER PLACED. | [5 empty] | Additional Codes
TO2 | RO10050143 | PO10008179 | 1 | Cancelled | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P06W | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-09-27 |  | 2018-06-01 |  | 2018-05-30 |  | 0 | 1.7 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N | 33 |  | zkeller | Natalie Papaeracleous | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10050143 | PO10006452 | 1 | Cancelled | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P06W | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-09-27 |  |  |  | 2018-05-30 |  | 0 | 1.7 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N | 33 |  | zkeller |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10050143 | PO10008178 | 2 | Cancelled | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P06W | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-09-27 | [5 empty] | 0 | 1.7 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N | 33 |  | zkeller |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10050143 | PO10006451 | 1 | Cancelled | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 103199FPA05P06W | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 30 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-10-25 |  |  |  | 2018-06-30 |  | 0 | 1.7 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N | 37 |  | zkeller |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10050143 | PO10008178 | 1 | Cancelled | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 103199FPA05P06W | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 30 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-10-25 | [5 empty] | 0 | 1.7 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N | 37 |  | zkeller |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10050143 | PO10008180 | 2 | Cancelled | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 103199FPA05P1CT | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 30 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N |  |  | zkeller |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10050143 | PO10008180 | 1 | Order Released for Fulfillment | Air | Direct Drop | China | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P1CT | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set [Guilin] | 2018-01-23 | 2018-08-31 | 2018-09-27 |  | 2018-09-27 | 2018-06-15 | 2018-05-30 |  | 92000 | 1.7 | 156400 | 72776.5 | 0 | 92000 | UNT | 1 Set | Set | 1 | N |  |  | zkeller |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10048132 |  | 2 | Cancelled |  |  |  | Mali |  | Other Non-Pharma | Medical Supplies | 102707XUZ09C | Syringe, Hypodermic, w/ Needle, 5 mL, Luer, 22G x 1.25 in, Sterile, 100 Each | 2018-01-10 | 2018-07-31 | [6 empty] | 960 | 4.5 | 4320 | 912 | 0 | 960 | PKG | 100 Each | Each | 100 | N |  |  | zkeller_rp |  | 313MISSION |  | Sent to FHI360 for sourcing approval | [5 empty] | Additional Codes
TO2 | RO10048132 |  | 1 | Cancelled |  |  |  | Mali |  | Other Non-Pharma | Medical Supplies | 102704XUZ09C | Syringe, Hypodermic, w/ Needle, 10 mL, Luer, 21G x 1.5 in, Sterile, 100 Each | 2018-01-10 | 2018-07-31 | [6 empty] | 960 | 5 | 4800 | 912 | 0 | 960 | PKG | 100 Each | Each | 100 | N |  |  | zkeller_rp |  | 313MISSION |  | Sent to FHI360 for sourcing approval | [5 empty] | Additional Codes
TO2 | RO10042198 | PO10007134 | 1 | Shipment Delivered | Air | Direct Drop | Switzerland | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08W0AF | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x1 Blister Pack Tablets [Novartis] | 2017-10-24 | 2018-06-30 | 2018-06-15 | 2018-06-07 | 2018-09-04 | 2018-04-06 | 2018-05-22 | 2018-04-27 | 20000 | 10.8 | 216000 | 263801.22 | 10000 | 0 | BOX | 30 x 6x1 Blister Pack Tablets | Treatment | 30 | N | 28 | WWWE136258313997 | amadady | Alberta Steven | 313MISSION | Malaria - Mission | PO-PENDING INSPECTION | AD012 | -15 | 2018-07-16 16:04 | Adjusted ADD to reflect approval attached. | https://chemonics.sharepoint.com/:b:/r/sites/FO000a/TO2_Procurement/Mali_TO2_RO10042198_ALU/Mission%20accepted%20early%20delivery%20PO10007134.pdf?csf=1&e=0yKMKd | Additional Codes
TO2 | RO10042198 | PO10007134 | 1 | Shipment Delivered | Air | Direct Drop | Switzerland | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08W0AF | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x1 Blister Pack Tablets [Novartis] | 2017-10-24 | 2018-06-30 | 2018-06-15 | 2018-06-07 | 2018-09-04 | 2018-04-06 | 2018-05-22 | 2018-04-27 | 20000 | 10.8 | 216000 | 263801.22 | 10000 | 0 | BOX | 30 x 6x1 Blister Pack Tablets | Treatment | 30 | N | 28 | WWWE136260392344 | amadady | Alberta Steven | 313MISSION | Malaria - Mission | PO-PENDING INSPECTION | AD012 | -15 | 2018-07-16 16:04 | Adjusted ADD to reflect approval attached. | https://chemonics.sharepoint.com/:b:/r/sites/FO000a/TO2_Procurement/Mali_TO2_RO10042198_ALU/Mission%20accepted%20early%20delivery%20PO10007134.pdf?csf=1&e=0yKMKd | Additional Codes
TO2 | RO10042198 | PO10007134 | 2 | Shipment Delivered | Air | Direct Drop | Switzerland | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08X0AF | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x2 Blister Pack Tablets [Novartis] | 2017-10-24 | 2018-06-30 | 2018-06-15 | 2018-06-07 | 2018-09-04 | 2018-04-06 | 2018-05-22 | 2018-04-27 | 23334 | 20.1 | 469013.4 | 263801.22 | 7778 | 0 | BOX | 30 x 6x2 Blister Pack Tablets | Treatment | 30 | N | 28 | WWWE136258313997 | amadady | Alberta Steven | 313MISSION | Malaria - Mission | PO-PENDING INSPECTION | AD012 | -15 | 2018-07-16 16:05 | Adjusted ADD to reflect approval attached. | https://chemonics.sharepoint.com/:b:/r/sites/FO000a/TO2_Procurement/Mali_TO2_RO10042198_ALU/Mission%20accepted%20early%20delivery%20PO10007134.pdf?csf=1&e=0yKMKd | Additional Codes
TO2 | RO10042198 | PO10007134 | 2 | Shipment Delivered | Air | Direct Drop | Switzerland | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08X0AF | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x2 Blister Pack Tablets [Novartis] | 2017-10-24 | 2018-06-30 | 2018-06-15 | 2018-07-19 | 2018-09-04 | 2018-04-06 | 2018-05-22 | 2018-04-27 | 23334 | 20.1 | 469013.4 | 263801.22 | 15556 | 0 | BOX | 30 x 6x2 Blister Pack Tablets | Treatment | 30 | N | 28 | WWWE136259517825 | amadady | Alberta Steven | 313MISSION | Malaria - Mission | PO-PENDING INSPECTION | AD012 | -15 | 2018-07-16 16:05 | Adjusted ADD to reflect approval attached. | https://chemonics.sharepoint.com/:b:/r/sites/FO000a/TO2_Procurement/Mali_TO2_RO10042198_ALU/Mission%20accepted%20early%20delivery%20PO10007134.pdf?csf=1&e=0yKMKd | Additional Codes
TO2 | RO10042198 | PO10007133 | 1 | Shipment Delivered | Air | Direct Drop | India | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAA08Z0WK | Artemether/Lumefantrine 20/120 mg Tablet, 30 x 6x4 Blister Pack Tablets [Macleods] | 2017-10-24 | 2018-06-30 | 2018-07-19 | 2018-07-19 | 2018-06-25 | 2018-03-12 | 2018-03-30 | 2018-04-25 | 6667 | 18 | 120006 | 263801.22 | 6667 | 0 | BOX | 30 x 6x4 Blister Pack Tablets | Treatment | 30 | N | 24 | WWWE136035648615 | amadady | Alberta Steven | 313MISSION | Malaria - Mission | PO-QA ONGOING | AD012 | -19 | 2018-07-27 15:48 | Mission requested early delivery | https://chemonics.sharepoint.com/:b:/r/sites/FO000a/TO2_Procurement/Mali_TO2_RO10042198_ALU/Mission%20accepted%20early%20delivery%20PO10007134.pdf?csf=1&e=bL9HXa | Additional Codes
TO2 | RO10042198 | PO10007133 | 2 | Shipment Delivered | Air | Direct Drop | India | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAA08Y0WK | Artemether/Lumefantrine 20/120 mg Tablet, 30 x 6x3 Blister Pack Tablets [Macleods] | 2017-10-24 | 2018-06-30 | 2018-07-19 | 2018-07-19 | 2018-06-25 | 2018-03-12 | 2018-03-30 | 2018-04-25 | 16667 | 15 | 250155 | 263801.22 | 16667 | 0 | BOX | 30 x 6x3 Blister Pack Tablets | Treatment | 30 | N | 24 | WWWE136035648615 | amadady | Alberta Steven | 313MISSION | Malaria - Mission |  | AD012 | -19 | 2018-07-27 15:49 | Mission requested early delivery | https://chemonics.sharepoint.com/:b:/r/sites/FO000a/TO2_Procurement/Mali_TO2_RO10042198_ALU/Mission%20accepted%20early%20delivery%20PO10007134.pdf?csf=1&e=bL9HXa | Additional Codes
TO2 | RO10042173 | PO10006469 | 1 | Shipment Delivered | Sea | Direct Drop | United Arab Emirates | Mali | Population Services Inc (PSI) | LLINs | Long Lasting Insecticide Treated Nets (LLINs) | 100054XLL01S03C | Long Lasting Insecticide Treated Net (LLIN) 180x190x170 cm (LxWxH) Rectangular (White), 1 Each [Tana] [Polyester] | 2017-10-23 | 2018-06-30 | 2018-06-30 | 2018-07-06 | 2018-06-12 | 2018-02-09 | 2018-03-30 | 2018-03-20 | 650000 | 1.93 | 1254500 | 237500 | 650000 | 0 | UNT | 1 Each | Each | 1 | N | 20 | WWWE132111593022 | skhederian | Marcus Hall | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10042173 | PO10006475 | 1 | Shipment Delivered | Sea | Direct Drop | United Arab Emirates | Mali | Population Services Inc (PSI) | LLINs | Long Lasting Insecticide Treated Nets (LLINs) | 100054XLL01S03C | Long Lasting Insecticide Treated Net (LLIN) 180x190x170 cm (LxWxH) Rectangular (White), 1 Each [Tana] [Polyester] | 2017-10-23 | 2018-06-30 | 2018-06-30 | 2018-06-16 | 2018-05-15 | 2018-02-09 | 2018-03-30 | 2018-03-22 | 650000 | 1.93 | 1254500 | 237500 | 650000 | 0 | UNT | 1 Each | Each | 1 | N |  | WWWE132119845899 | skhederian | Marcus Hall | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10042172 |  | 3 | Cancelled |  |  |  | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set | 2017-10-23 | 2018-07-31 | [6 empty] | 192000 | 1.74 | 334080 | 66816 | 0 | 192000 | UNT | 1 Set | Set | 1 | N |  |  | zkeller_rp |  | 313MISSION | Malaria - Mission | Mission Changed order details- Pending revised CPIR 11/30.12/05 | [5 empty] | Additional Codes
TO2 | RO10042171 | PO10005718 | 1 | Cancelled | Air | Direct Drop | Netherlands | Mali |  | Other Pharma | Malaria Pharmaceuticals | 100098AXH09I0BO | Amodiaquine 75 mg + Sulfadoxine/Pyrimethamine 250/12.5 mg Dispersible Tablets, 25 x 1 SP + 3 AQ Co-Blister Tablets [Guilin] | 2017-10-23 | 2018-06-30 | 2018-07-03 | [5 empty] | 0 | 16.6 | 0 | 0 | 0 | 0 | UNT | 25 x 1 SP + 3 AQ Co-Blister Tablets | Treatment | 25 | N | 30 |  | wcsadmin |  | 313MISSION | Malaria - Mission |  | AD014 |  | 2017-12-05 09:32 | Changed to the item SKU |  | Additional Codes
TO2 | RO10042171 | PO10005726 | 1 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Pharma | Malaria Pharmaceuticals | 102123AXH0DP0BO | Amodiaquine 76.5 mg + Sulfadoxine/Pyrimethamine 250/12.5 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets [Guilin] | 2017-10-23 | 2018-07-31 | 2018-07-03 | 2018-09-19 | 2018-09-07 | 2017-12-28 | 2018-07-05 |  | 20000 | 16.6 | 332000 | 0 | 20000 | 0 | PKG | 50 x 1 SP + 3 AQ Co-Blister Tablets | Treatment | 50 | N |  | WWWE148602542899 | wcsadmin | Natalie Papaeracleous | 313MISSION | Malaria - Mission | PO-ORDER PLACED. | [5 empty] | Additional Codes
TO2 | RO10042171 |  | 3 | Cancelled | Air | Direct Drop | Netherlands | Mali |  | Other Pharma | Malaria Pharmaceuticals | 102123AXH0DP0BO | Amodiaquine 76.5 mg + Sulfadoxine/Pyrimethamine 250/12.5 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets [Guilin] | 2017-10-23 |  | 2018-07-03 | [5 empty] | 0 | 16.6 | 0 | 0 | 0 | 0 | PKG | 50 x 1 SP + 3 AQ Co-Blister Tablets | Treatment | 50 | N |  |  | wcsadmin |  | 313MISSION | Malaria - Mission | [6 empty] | Additional Codes
TO2 | RO10042169 | RO10042169_1 | 2 | Shipment Delivered | Air | RDC | Belgium | Mali |  | SP | Malaria Pharmaceuticals | 100041AAA08A04B | Sulfadoxine/Pyrimethamine 500/25 mg Tablet, 1000 Tablets [Jiangsu Pengyao] | 2017-10-23 | 2018-06-30 | 2018-07-02 | 2018-07-02 | 2018-06-21 | 2018-02-12 | 2018-02-12 | 2018-02-14 | 2000 | 31.43 | 62860 | 14448 | 2000 | 0 | BOT | 1000 Tablets | Tablet | 1000 | N | 12 | WWWE130395658121 | dvijeyakumar | Zane Keller | 313MISSION | Malaria - Mission |  | AD050 | 33 | 2018-07-19 13:05 | There was a two week delay after we received early delivery approval (4/25/18 - 5/11/18) as a result of incorrect submission of the waiver by the Mission. | https://chemonics.sharepoint.com/sites/FO000/GSC/WorkingDocuments/Forms/AllItems.aspx?viewpath=%2Fsites%2FFO000%2FGSC%2FWorkingDocuments%2FForms%2FAllItems%2Easpx&id=%2Fsites%2FFO000%2FGSC%2FWorkingDocuments%2FCOR%20Approvals%20for%20Reason%20Co | Additional Codes
TO2 | RO10042167 | PO10007357 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-10-23 | 2018-04-30 | 2018-06-20 | 2018-06-20 | 2018-07-09 | 2018-03-12 | 2018-04-16 | 2018-04-20 | 120000 | 10.75 | 1290000 | 516000 | 16900 | 40237 | BOX | 25 Tests | Test | 25 | N | 17 | WWWE135443897856 | jbrown |  | 313MISSION | Malaria - Mission | PO-QA ONGOING. | AD050 | 8 | 2018-07-19 15:53 | Mali Warehouse could not accept any shipments. COR approval received via COR Tracker. | https://chemonics.sharepoint.com/:f:/r/sites/FO000/GSC/WorkingDocuments/02.%20Source/TO2%20AD%20Change%20Requests?csf=1&e=pME6c3 | Additional Codes
TO2 | RO10042167 | PO10007357 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-10-23 | 2018-04-30 | 2018-06-20 | 2018-06-20 | 2018-07-09 | 2018-03-12 | 2018-04-16 | 2018-04-20 | 120000 | 10.75 | 1290000 | 516000 | 16871 | 40237 | BOX | 25 Tests | Test | 25 | N | 17 | WWWE135454331455 | jbrown |  | 313MISSION | Malaria - Mission | PO-QA ONGOING. | AD050 | 8 | 2018-07-19 15:53 | Mali Warehouse could not accept any shipments. COR approval received via COR Tracker. | https://chemonics.sharepoint.com/:f:/r/sites/FO000/GSC/WorkingDocuments/02.%20Source/TO2%20AD%20Change%20Requests?csf=1&e=pME6c3 | Additional Codes
TO2 | RO10042167 | PO10007357 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-10-23 | 2018-04-30 | 2018-06-20 | 2018-06-20 | 2018-07-09 | 2018-03-12 | 2018-04-16 | 2018-04-20 | 120000 | 10.75 | 1290000 | 516000 | 34992 | 40237 | BOX | 25 Tests | Test | 25 | N | 17 | WWWE135455065602 | jbrown |  | 313MISSION | Malaria - Mission | PO-QA ONGOING. | AD050 | 8 | 2018-07-19 15:53 | Mali Warehouse could not accept any shipments. COR approval received via COR Tracker. | https://chemonics.sharepoint.com/:f:/r/sites/FO000/GSC/WorkingDocuments/02.%20Source/TO2%20AD%20Change%20Requests?csf=1&e=pME6c3 | Additional Codes
TO2 | RO10042167 | PO10007357 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-10-23 | 2018-04-30 | 2018-06-20 | 2018-06-20 | 2018-07-09 | 2018-03-12 | 2018-04-16 | 2018-04-20 | 120000 | 10.75 | 1290000 | 516000 | 11000 | 40237 | BOX | 25 Tests | Test | 25 | N | 17 | WWWE135455070074 | jbrown |  | 313MISSION | Malaria - Mission | PO-QA ONGOING. | AD050 | 8 | 2018-07-19 15:53 | Mali Warehouse could not accept any shipments. COR approval received via COR Tracker. | https://chemonics.sharepoint.com/:f:/r/sites/FO000/GSC/WorkingDocuments/02.%20Source/TO2%20AD%20Change%20Requests?csf=1&e=pME6c3 | Additional Codes
TO2 | RO10036105 | PO10003626 | 1 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Pharma | Malaria Pharmaceuticals | 102124AXH0DP0BO | Amodiaquine 153 mg + Sulfadoxine/Pyrimethamine 500/25 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets [Guilin] | 2017-07-24 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 2018-04-23 | 2017-09-21 | 2018-01-08 | 2017-12-21 | 40000 | 18.25 | 730000 | 219000 | 39960 | 40 | PKG | 50 x 1 SP + 3 AQ Co-Blister Tablets | Treatment | 50 | N |  | WWWE128142933196 | eadiang |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10035195 | RO10035195_2 | 5 | Shipment Delivered | Air | RDC | Belgium | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-04-30 | 2018-07-19 | 2018-07-19 | 2018-07-31 | 2018-04-17 | 2018-04-17 |  | 28 | 0 | 0 | 129000 | 28 | 0 | BOX | 25 Tests | Test | 25 | N |  | WWWE136158687981 | mgurung | Jesse Brown | 313MISSION | Malaria - Mission |  | AD015 | 15 | 2018-08-01 14:58 | Warehouse delay | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | PO10005341 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-02-28 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2017-11-15 | 2017-12-27 | 2018-02-07 | 40000 | 10.75 | 430000 | 129000 | 14193 | 0 | BOX | 25 Tests | Test | 25 | N | 12 | WWWE129640902975 | mgurung |  | 313MISSION | Malaria - Mission | PO-SCHEDULING INSPECTION | AD015 |  | 2018-08-01 14:58 | Warehouse delay | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | PO10005341 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-02-28 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2017-11-15 | 2017-12-27 | 2018-02-07 | 40000 | 10.75 | 430000 | 129000 | 12903 | 0 | BOX | 25 Tests | Test | 25 | N | 12 | WWWE134410576517 | mgurung |  | 313MISSION | Malaria - Mission | PO-SCHEDULING INSPECTION | AD015 |  | 2018-08-01 14:58 | Warehouse delay | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | PO10005341 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-02-28 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2017-11-15 | 2017-12-27 | 2018-02-07 | 40000 | 10.75 | 430000 | 129000 | 12904 | 0 | BOX | 25 Tests | Test | 25 | N | 12 | WWWE134410584141 | mgurung |  | 313MISSION | Malaria - Mission | PO-SCHEDULING INSPECTION | AD015 |  | 2018-08-01 14:58 | Warehouse delay | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | RO10035195_1 | 3 | Shipment Delivered | Air | RDC | Belgium | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-04-30 | 2018-07-19 | 2018-07-19 | 2018-07-04 | 2018-04-17 | 2018-04-16 | 2018-04-27 | 80000 | 10.75 | 860000 | 129000 | 20736 | 1 | BOX | 25 Tests | Test | 25 | N | 33 | WWWE136157948776 | mgurung | Jesse Brown | 313MISSION | Malaria - Mission |  | AD015 | 49 | 2018-08-01 14:58 | Warehouse was unable to receive the goods. | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | RO10035195_1 | 3 | Shipment Delivered | Air | RDC | Belgium | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-04-30 | 2018-07-19 | 2018-07-19 | 2018-07-04 | 2018-04-17 | 2018-04-16 | 2018-04-27 | 80000 | 10.75 | 860000 | 129000 | 20156 | 1 | BOX | 25 Tests | Test | 25 | N | 33 | WWWE136158687981 | mgurung | Jesse Brown | 313MISSION | Malaria - Mission |  | AD015 | 49 | 2018-08-01 14:58 | Warehouse was unable to receive the goods. | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | RO10035195_1 | 3 | Shipment Delivered | Air | RDC | Belgium | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-04-30 | 2018-07-19 | 2018-07-19 | 2018-07-04 | 2018-04-17 | 2018-04-16 | 2018-04-27 | 80000 | 10.75 | 860000 | 129000 | 18371 | 1 | BOX | 25 Tests | Test | 25 | N | 33 | WWWE136164319766 | mgurung | Jesse Brown | 313MISSION | Malaria - Mission |  | AD015 | 49 | 2018-08-01 14:58 | Warehouse was unable to receive the goods. | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | RO10035195_1 | 3 | Shipment Delivered | Air | RDC | Belgium | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-04-30 | 2018-07-19 | 2018-07-19 | 2018-07-04 | 2018-04-17 | 2018-04-16 | 2018-04-27 | 80000 | 10.75 | 860000 | 129000 | 20736 | 1 | BOX | 25 Tests | Test | 25 | N | 33 | WWWE136165064053 | mgurung | Jesse Brown | 313MISSION | Malaria - Mission |  | AD015 | 49 | 2018-08-01 14:58 | Warehouse was unable to receive the goods. | https://chemonics.sharepoint.com/:f:/r/sites/FO000a/TO2_Procurement/Mali_RDT_TO2_RO10035195_2017/10_Approvals/ADD%20change?csf=1&e=NZqKfP | Additional Codes
TO2 | RO10035195 | PO10005342 | 1 | Cancelled | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100062XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2017-07-21 | 2018-04-30 | 2018-07-04 |  | 2018-04-27 | 2017-11-15 | 2018-02-28 |  | 0 | 10.75 | 0 | 0 | 0 | 0 | BOX | 25 Tests | Test | 25 | N | 33 |  | mgurung |  | 313MISSION | Malaria - Mission | PO-ORDER PLACED. | [5 empty] | Additional Codes
TO2 | RO10023320 | PO10001172 | 2 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Non-Pharma | Others | 102048XUZ01S0KM | Kitting Fee, 1 Each [IDA] | 2016-05-24 | 2017-02-28 | 2017-08-31 | 2017-09-19 | 2017-09-13 | 2017-02-23 | 2017-05-22 |  | 1 | 26400 | 26400 | 9303.35 | 1 | 0 | UNT | 1 Each | Each | 1 | N |  | WWWE109022039969 | cshumricksourcingapprover |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10023320 | PO10001172 | 1 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P0KN | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set [Guilin] | 2016-05-24 | 2017-02-28 | 2017-08-31 | 2017-09-19 | 2017-09-13 | 2017-02-23 | 2017-04-30 |  | 96000 | 1.84 | 176640 | 9303.35 | 95940 | 60 | UNT | 1 Set | Set | 1 | N |  | WWWE109022039969 | cshumricksourcingapprover |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10023320 | PO10001172 | 4 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Non-Pharma | Medical Supplies | 101012XUZ09C0KN | Syringe, With Needle, Luer Slip, 5 mL, 21G x 1 1/2 in, 100 Each [Guilin] | 2016-05-24 | 2017-02-28 | 2017-08-31 | 2017-09-19 | 2017-09-13 | 2017-02-23 | 2017-05-22 |  | 480 | 2.52 | 1209.6 | 9303.35 | 480 | 0 | PKG | 100 Each | Each | 100 | N |  | WWWE109022039969 | cshumricksourcingapprover |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10023320 | PO10001172 | 3 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Non-Pharma | Medical Supplies | 102047XUZ09C0KN | Syringe, With Needle, Luer Slip, 10 mL, 21G x 1 1/2 in, 100 Each [Guilin] | 2016-05-24 | 2017-02-28 | 2017-08-31 | 2017-09-19 | 2017-09-13 | 2017-02-23 | 2017-05-22 |  | 480 | 3.78 | 1814.4 | 9303.35 | 480 | 0 | PKG | 100 Each | Each | 100 | N |  | WWWE109022039969 | cshumricksourcingapprover |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10016211 | PO10000482 | 1 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Pharma | Malaria Pharmaceuticals | 100098AXH0DP0AW | Amodiaquine 75 mg + Sulfadoxine/Pyrimethamine 250/12.5 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets [Guilin] | 2016-07-07 | 2017-02-01 | 2017-04-01 | 2017-06-29 | 2017-07-05 | 2017-03-06 | 2017-03-28 | 2017-04-13 | 35957 | 17.1 | 614864.7 | 90211.38 | 35957 | 0 | UNT | 50 x 1+3 Co-Blister Tablets | Treatment | 50 | N |  | WWWE104277899717 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10016211 | PO10000483 | 1 | Shipment Delivered | Air | Direct Drop | Netherlands | Mali |  | Other Pharma | Malaria Pharmaceuticals | 100099AXH0DP0BN | Amodiaquine 150 mg + Sulfadoxine/Pyrimethamine 500/25 mg Dispersible Tablets, 50 x 1 SP + 3 AQ Co-Blister Tablets [Guilin] | 2016-07-07 | 2017-02-01 | 2017-04-01 | 2017-08-02 | 2017-06-06 | 2017-03-06 | 2017-02-17 |  | 60000 | 18.65 | 1119000 | 90211.38 | 60000 | 0 | UNT | 50 x 1+3 Co-Blister Tablets | Treatment | 50 | N |  | WWWE106412669668 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010291 | PO10000565 | 2 | Shipment Delivered | Air | Direct Drop | India | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08W00K | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x1 Blister Pack Tablets [Ajanta] | 2016-05-24 | 2017-02-01 | 2017-02-28 | 2017-04-06 | 2017-04-06 | 2017-02-08 | 2016-11-30 |  | 23334 | 11.25 | 262507.5 | 29549 | 13083 | 10251 | BOX | 30 x 6x1 Blister Pack Tablets | Treatment | 30 | N |  | WWWE100243541221 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010291 | PO10000565 | 4 | Shipment Delivered | Air | Direct Drop | India | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08X00K | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x2 Blister Pack Tablets [Ajanta] | 2016-05-24 | 2017-02-01 | 2017-02-28 | 2017-04-06 | 2017-04-06 | 2017-02-08 | 2016-11-30 | 2017-02-19 | 26667 | 22 | 586674 | 29549 | 26667 | 0 | BOX | 30 x 6x2 Blister Pack Tablets | Treatment | 30 | N |  | WWWE102777723663 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010291 | PO10000565 | 1 | Shipment Delivered | Air | Direct Drop | India | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAA08Z00K | Artemether/Lumefantrine 20/120 mg Tablet, 30 x 6x4 Blister Pack Tablets [Ajanta] | 2016-05-24 | 2017-02-01 | 2017-02-28 | 2017-04-06 | 2017-04-06 | 2017-02-08 | 2016-11-30 | 2017-02-19 | 13334 | 25.29 | 337216.86 | 29549 | 13334 | 0 | BOX | 30 x 6x4 Blister Pack Tablets | Treatment | 30 | N |  | WWWE102778260478 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010291 | PO10000565 | 3 | Shipment Delivered | Air | Direct Drop | India | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAA08Y00K | Artemether/Lumefantrine 20/120 mg Tablet, 30 x 6x3 Blister Pack Tablets [Ajanta] | 2016-05-24 | 2017-02-01 | 2017-02-28 | 2017-04-06 | 2017-04-06 | 2017-02-08 | 2016-11-30 | 2017-02-19 | 13334 | 19.98 | 266413.32 | 29549 | 3822 | 9512 | BOX | 30 x 6x3 Blister Pack Tablets | Treatment | 30 | N |  | WWWE102778261498 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010193 |  | 1 | Cancelled | Air |  |  | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08W | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x1 Blister Pack Tablets | 2016-10-07 | 2017-02-01 | [6 empty] | 23334 | 14.09 | 328776.06 | 111020.41 | 0 | 23334 | BOX | 30 x 6x1 Blister Pack Tablets | Treatment | 30 | N |  |  | mlto2buyer | [9 empty] | Additional Codes
TO2 | RO10010193 |  | 2 | Cancelled | Air |  |  | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAK08X | Artemether/Lumefantrine 20/120 mg Dispersible Tablet, 30 x 6x2 Blister Pack Tablets | 2016-10-07 | 2017-02-01 | [6 empty] | 26667 | 28.19 | 751742.73 | 111020.41 | 0 | 26667 | BOX | 30 x 6x2 Blister Pack Tablets | Treatment | 30 | N |  |  | mlto2buyer | [9 empty] | Additional Codes
TO2 | RO10010193 |  | 3 | Cancelled | Air |  |  | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAA08Y | Artemether/Lumefantrine 20/120 mg Tablet, 30 x 6x3 Blister Pack Tablets | 2016-10-07 | 2017-02-01 | [6 empty] | 13334 | 13.49 | 179875.66 | 111020.41 | 0 | 13334 | BOX | 30 x 6x3 Blister Pack Tablets | Treatment | 30 | N |  |  | mlto2buyer | [9 empty] | Additional Codes
TO2 | RO10010193 |  | 4 | Cancelled | Air |  |  | Mali |  | ACTs | Malaria Pharmaceuticals | 100076AAA08Z | Artemether/Lumefantrine 20/120 mg Tablet, 30 x 6x4 Blister Pack Tablets | 2016-10-07 | 2017-02-01 | [6 empty] | 13334 | 16.49 | 219877.66 | 111020.41 | 0 | 13334 | BOX | 30 x 6x4 Blister Pack Tablets | Treatment | 30 | N |  |  | mlto2buyer | [9 empty] | Additional Codes
TO2 | RO10010188 | PO10000626 | 1 | Shipment Delivered | Air | Direct Drop | South Korea | Mali |  | mRDTs | Malaria Rapid Diagnostic Test (RDTs) | 100064XXC08D04A | Malaria Rapid Diagnostic Test (RDT) HRP2 (Pf) Cassette, 25 Tests [Standard Diagnostics] [Ag Pf] | 2016-05-24 | 2017-02-01 | 2017-02-01 | 2017-01-24 | 2017-01-24 | 2017-01-09 | 2017-01-09 |  | 120000 | 10.75 | 1290000 | 181722 | 120000 | 0 | BOX | 25 Tests | Test | 25 | N |  | WWWE102772647450 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010162 |  | 1 | Cancelled | Air |  |  | Mali |  | SP | Malaria Pharmaceuticals | 100041AAA08A | Sulfadoxine/Pyrimethamine 500/25 mg Tablet, 1000 Tablets | 2016-05-24 | 2017-02-03 | [6 empty] | 6000 | 32.97 | 197820 | 59346 | 0 | 6000 | BOT | 1000 Tablets | Tablet | 1000 | N |  |  | mlto2buyer | [9 empty] | Additional Codes
TO2 | RO10010161 | PO10000851 | 1 | Cancelled | Air | Direct Drop | Netherlands | Mali |  | Severe Malaria Meds | Malaria Pharmaceuticals | 100097FPA05P0KN | Artesunate (w/ 1 Amp NaHCO3 5% + 1 Amp NaCl 0.9%) 60 mg Vial, 1 Set [Guilin] | 2016-05-24 | 2017-02-03 | 2017-08-30 | [5 empty] | 0 | 1.84 | 0 | 0 | 0 | 0 | UNT | 1 Set | Set | 1 | N |  |  | zkeller |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010161 | PO10000851 | 2 | Cancelled | Air | Direct Drop | Netherlands | Mali |  | Other Non-Pharma | Medical Supplies | 101012XUZ09C0KN | Syringe, With Needle, Luer Slip, 5 mL, 21G x 1 1/2 in, 100 Each [Guilin] | 2016-05-24 | 2017-02-03 | 2017-08-30 | [5 empty] | 0 | 2.52 | 0 | 0 | 0 | 0 | PKG | 100 Each | Each | 100 | N |  |  | zkeller |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010161 | PO10000851 | 3 | Cancelled | Air | Direct Drop | Netherlands | Mali |  | Other Non-Pharma | Medical Supplies | 102047XUZ09C0KN | Syringe, With Needle, Luer Slip, 10 mL, 21G x 1 1/2 in, 100 Each [Guilin] | 2016-05-24 | 2017-02-03 | 2017-08-30 | [5 empty] | 0 | 3.78 | 0 | 0 | 0 | 0 | PKG | 100 Each | Each | 100 | N |  |  | zkeller |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10010155 | PO10000277 | 1 | Shipment Delivered | Sea | Direct Drop | United Arab Emirates | Mali |  | LLINs | Long Lasting Insecticide Treated Nets (LLINs) | 100054XXW01S03C | Long Lasting Insecticide Treated Net (LLIN) 180x190x170 cm (LxWxH) Rectangular Polyester (White), 1 Each [Tana] | 2016-05-24 | 2017-02-01 | 2017-03-30 | 2017-04-28 | 2017-03-30 | 2016-12-22 | 2017-01-30 | 2016-12-26 | 1250000 | 1.93 | 2412500 | 482500 | 1214250 | 35750 | UNT | 1 Each | Each | 1 | N |  | WWWE96645808596 | mlto2buyer |  | 313MISSION | [7 empty] | Additional Codes
TO2 | RO10009132 |  | 2 | Cancelled | Air |  |  | Mali |  |  |  | UNKNOWN |  | 2016-10-07 | 2017-02-01 | [6 empty] | 1797820 | 9.14 | 16432074.8 | 6420311.22 | 0 | 1797820 | BOX |  |  |  | N |  |  | mlto2buyer | [9 empty] | Additional Codes
TO2 | RO10009132 |  | 1 | Cancelled | Air |  |  | Mali |  |  |  | UNKNOWN |  | 2016-10-07 | 2017-02-01 | [6 empty] | 3000000 | 8.79 | 26370000 | 6420311.22 | 0 | 3000000 | BOX |  |  |  | N |  |  | mlto2buyer | [9 empty] | Additional Codes

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only